ADLM STUDIO

ADLM Website — Project Workspace Feature Documentation

What you can do on the ADLM web platform after saving a project from the desktop plugins (QUIV / HERON / CIVIQ / Revit MEP).

This document is the definitive feature reference for everything that happens after a takeoff is saved to the cloud: rate generation, the Bill of Quantities, material & labour schedules with pricing, the variation tracker, the contract tracker, interim valuation & payment certificates, the Work Breakdown Structure (WBS), cost-to-WBS linking, and earned-value project controls. Every feature described here is implemented in the current codebase.

Feature reference — generated from the current product codebase

# Table of Contents

# 1. The big picture

The ADLM Website is the cloud workspace and quantity-surveying brain that sits behind the ADLM desktop takeoff plugins. The workflow is:

Desktop model ADLM Cloud (this website) Outputs ┌────────────────┐ ┌──────────────────────────────┐ ┌──────────────────┐ │ Revit / PlanSwift│ save │ Priced BOQ → Rate Gen │ │ Excel BOQ │ │ / Civil 3D model │─────▶│ Material/Labour schedules │───▶│ Payment certs │ │ (QUIV/HERON/ │ open │ Contract + Variation tracker │ │ Final account │ │ CIVIQ plugins) │◀─────│ WBS + EVM project controls │ │ Public dashboard │ └────────────────┘ from └──────────────────────────────┘ └──────────────────┘ cloud

A takeoff done in the plugin is saved to the cloud as a project. On the website that project becomes a fully editable, priced Bill of Quantities, which then drives everything downstream: rates, schedules, the contract baseline, variations, payment certificates, the work programme (WBS), and earned-value reporting — all sharable with the client through a live read-only dashboard. Changes made on the web can be pulled back into the plugin via Open from Cloud, so the model and the commercial data stay in step.

The platform is Naira-native (NGN) and built around Nigerian QS practice — BESMM4 preliminaries, NRM2 / SMM7 work-section structure, and the Nigerian BOQ serial-letter convention.

# 2. The plugin suite & how projects arrive

## 2.1 The plugins and what they map to

Each desktop plugin is a different takeoff source. Internally the platform identifies the source by a productKey, and the discipline (structural/architectural vs services) follows from it:

| Brand name | Platform | productKey | Discipline categories produced |
| --- | --- | --- | --- |
| QUIV | Autodesk Revit (Architectural/Structural) | revit | Substructure · Frames · Superstructure |
| HERON | PlanSwift | planswift | Substructure · Frames · Superstructure |
| CIVIQ | Autodesk Civil 3D | civil3d | Substructure · Frames · Superstructure |
| Revit MEP | Autodesk Revit (Services) | revitmep | HVAC · Plumbing · Electrical |

Naming note: in the code the services split is driven by whether the product key contains mep. QUIV/HERON/CIVIQ all produce the structural/architectural category set (Substructure/Frames/Superstructure); the MEP plugin produces the services set (HVAC/Plumbing/Electrical). Each plugin also has a paired materials mode (e.g. revit-materials) used for the material/labour schedule.

Every project — whatever the source plugin — lives in one unified project model and gains the same downstream toolset (BOQ, rates, contract, variations, certificates, WBS, EVM). The plugin only determines the takeoff content and the default classification set.

## 2.2 Saving a project (the save flow)

When a user clicks Save to Cloud in a plugin, the plugin signs in to the ADLM API and posts the takeoff:

- The project is created/updated through the ADLM API (no direct database access from the plugin).

- Entitlement-gated: the save only succeeds if the user holds an active subscription for that plugin. Expired or missing subscriptions are rejected with a clear "No active subscription" / "Subscription expired" message.

- What's saved: the project name, the takeoff items (each line: description, quantity, unit, rate, level/floor, type/code, and the Revit element IDs behind it), plus model identity metadata so re-saves update the same project instead of duplicating it.

- Safe re-saves: every save carries a version number. If two edits collide, the platform returns a version conflict rather than silently overwriting — so cloud edits and plugin re-saves never clobber each other.

- Auto-classification on arrival: each item is automatically tagged with a Category (building element) and a Trade (work section) if the plugin didn't supply one, so the BOQ is organised the moment it lands.

There is also a unified save path that, in one call, persists both the priced takeoff and its derived material/labour schedule (the QUIV material-rate upgrade), returning a proposed-vs-actual profit-margin summary.

## 2.3 Open from Cloud

Every project shows a copyable Project ID. Pasting that ID into the plugin's Open from Cloud dialog pulls the cloud project (including any rates and edits made on the web) back into the desktop model — the round-trip that keeps the model and the commercial data synchronised.

# 3. The project workspace

## 3.1 The project explorer

After saving, the user lands in the project explorer for that plugin — a folder-card grid where each saved project is a card showing:

- Project name and a 📁 folder icon

- Item count (number of takeoff lines)

- Last-updated timestamp

- Roll-up totals at the section header: total cost, valued amount, progress

The most recently saved project appears at the top. Cards support multi-select, per-card delete, "delete selected" and "delete all". Clicking a card opens the project.

## 3.2 The four working tabs

Opening a project reveals four tabs — the heart of the workspace:

| Tab | Purpose |
| --- | --- |
| Dashboard | Progress and cost summary at a glance — gross value, valued (earned) amount, remaining, % complete |
| Bill of Quantity | The main work surface: priced line items, rate application, categories/trades, preliminaries, PC sums, variations, contract lock |
| PM Dashboard | The work programme: WBS/tasks, schedule, earned-value (EVM) metrics, risk register, issue log |
| Valuation | Interim payment certificates, the daily valuation log, retention/VAT/WHT settings |

The header also surfaces the Project ID (for Open from Cloud), a contract lock/draft badge, and a Share Dashboard control that produces a public client link.

# 4. Bill of Quantities (BOQ)

The BOQ is generated automatically from the saved takeoff and presented as a fully editable, priced bill. It is the central artefact from which rates, schedules, the contract, and certificates all flow.

## 4.1 The BOQ work surface

The bill is a spreadsheet-grade table. Columns:

S/N · Status (✓ + % complete) · Description · Qty · Unit · Rate · (optional Actual qty / Actual rate / Actual amount) · Gross amount · Deducted (earned) · Balance (outstanding) · Actions

- Columns are drag-resizable; rows are drag-reorderable; every column is sortable.

- Quantity and unit are read-only (they come straight from the takeoff — the single source of truth for measurement).

- Description carries an inline category/trade reclassification dropdown and a WBS-link health chip.

## 4.2 Applying rates (the smart rate cell)

The rate cell is where pricing happens, and it is deliberately powerful:

- Excel-style formula entry — type = to enter a formula, e.g. =1.2*1.5*95000, with a live preview. Only arithmetic is allowed (safe-evaluated, not raw eval). % is understood as /100.

- Rate-library search — type a name instead of a number and the cell searches the Rate Generation library, suggesting matching built-up rates. Picking one fills the rate.

- Automatic unit conversion — when a suggested rate's unit differs from the item's (m² ↔ m via a slab thickness parsed from the description, tonne ↔ kg, m³ → m²), the rate is converted automatically; genuine mismatches are flagged amber.

- Group linking — link similar items so a rate change on one propagates to the whole group (e.g. all "150mm blockwork" lines at once).

- Lock-aware — once the contract is locked, the rate cell becomes a read-only 🔒 chip and cannot be edited (see Contract Tracker).

## 4.3 Earned-value per line

Each line has a binary status tick and a % complete field. From these the bill computes, per row:

Gross = qty × rate Deducted (earned) = Gross × valuationFactor (valuationFactor = 1 if ratified, else %/100) Balance (outstanding) = Gross × (1 − valuationFactor)

So the BOQ doubles as a live value-of-work-done tracker. Optional Actual qty / Actual rate columns let the QS record re-measured values post-construction.

## 4.4 Organisation: categories, trades & sections

Items group two ways, toggled live:

- By Category (building element): Substructure / Frames / Superstructure (structural) or HVAC / Plumbing / Electrical (MEP).

- By Trade (NRM2/SMM7 work section): Earthworks, Concrete Works, Formwork, Reinforcement, Masonry, Damp-proofing, Carpentry & Roofing, Joinery, Finishes (Floor/Wall/Ceiling), Decoration, Structural Steelwork, External Works — or HVAC / Plumbing & Drainage / Electrical Installations for MEP.

Each group renders a banner header, its items, and a subtotal row. A Summary by category card tabulates items/gross/deducted/balance per group with a grand total. Users can reclassify any line inline, and trade reclassifications train a self-learning classifier so future takeoffs are categorised better.

A sticky Section Rail (and a collapsible Office-style ribbon) gives instant jump-to-section navigation — important on bills with hundreds of lines.

## 4.5 Preliminaries, provisional sums, contingency & tax

Beyond the measured lines, the bill carries the full QS grand-summary scope:

- Preliminaries — a standard BESMM4 22-item checklist (seeded automatically), each item with an allocation %, a "done" tick, and an actual ₦ column showing variance vs planned.

- Provisional / PC Sums — described lump sums with a "done" tick.

- Variations — change orders (see Variation Tracker).

These roll up through the standard cascade (all percentages editable inline; defaults shown):

Preliminary amount = (Gross + Provisional) × 7.5% BOQ subtotal = Gross + Provisional + Preliminary Contingency amount = BOQ subtotal × 5% VAT = (BOQ subtotal + Contingency) × 7.5% Planned project total = BOQ subtotal + Contingency + VAT Project total = Planned project total + Variations

A multi-step undo bar keeps the last five deletions (measured/prelim/PC/variation) individually restorable.

## 4.6 Exporting the BOQ

The Export menu offers several professionally formatted outputs (all Excel):

| Export | Structure |
| --- | --- |
| Elemental BOQ (Bungalow / Multi-storey) | One sheet per building element — Preliminaries, Substructure, Superstructure, Frame (split by floor), Staircase, External Works — plus Cover, Provisional Sums, Variations, "Other items", and a General Summary |
| Trade BOQ (NRM2-style, Bungalow / Multi-storey) | A single trade-structured sheet with per-trade sections and subtotals, plus separate Preliminaries / PC / Variations and a General Summary |
| Generic BOQ (by category / by trade) | A flat bill that mirrors exactly what's on screen, including unsaved rates |

The elemental/trade exports are formula-driven — every amount is a live Excel formula (Amount = qty × rate), so a recipient can change a rate and the workbook recalculates. They follow Nigerian BOQ conventions including the A-B-C…(skip I)…J-K serial-letter column, BESMM4 preliminaries, SMM work-section codes (E10 concrete / E20 formwork / E30 reinforcement), and standards references (BS 4449/4483 rebar, BS 5950 steelwork). The exporter intelligently handles foundation type (pad/raft/pile) and splits multi-storey frame elements per floor level. Empty elements are omitted, so there are no blank sheets.

# 5. Rate Generation engine

"Rate Gen" is the pricing brain. It builds a unit rate (price per m², m³, m, Nr…) for a work item by summing the per-unit cost of its materials and labour, then adding overhead and profit. These rates feed directly into the BOQ rate cell.

## 5.1 The rate build-up formula

A rate is composed from its breakdown of material + labour lines:

Net cost = Σ (line quantity × line unit price) ← quantity includes any wastage/conversion factor Overhead = Net cost × Overhead% (default 10%) Profit = Net cost × Profit% (default 25%) Total cost = Net cost + Overhead + Profit

Both overhead and profit are taken on the net cost (not compounded). Wastage isn't a separate line — it's folded into each component's quantity as a multiplier (e.g. ×1.4). This same formula is applied identically when authoring a rate, when computing one on demand, and when the plugin reads it back, so the number never drifts between surfaces.

The rate authoring screen supports spreadsheet-style formulas in unit-price fields (a line can be priced as =3% * Net Cost, and the engine iterates until interdependent formulas converge).

## 5.2 Three layers: master, override, custom

Rates are layered so a shared catalogue can be personalised per user:

- Master rates — the shared, admin-curated catalogue.

- User overrides — a user's personal edit of an existing master rate. An override fully replaces the master rate for that item.

- Custom rates — brand-new rates a user builds themselves (purely additive).

Precedence: user override > master, with custom rates appended. The "effective rates" a user actually prices against is the merged result. All edits are version-guarded so concurrent edits don't clobber each other.

Rates are organised into canonical sections: Groundwork, Concrete Works, Blockwork, Finishes, Roofing, Windows & Doors, Painting, Steelwork, Carbon & Others. Underneath sits a shared master component catalogue of materials and labour (each with a serial number, name, unit, and default unit price) that the build-ups reference.

## 5.3 Guardrails & integrity

- Composition guardrail — when a rate is saved, the platform checks that the stated headline total equals its build-up (within a 0.5% tolerance). An overstated rate (headline > build-up) is rejected/clamped down to the build-up, so an inflated rate can never reach the plugin.

- Price provenance (priceAsOf) — every breakdown line records which master material/labour row it came from (serial number + name) and when that price was captured. This provenance is carried through overrides and custom rates too, giving full traceability from a unit rate back to the dated source price.

- Component classification — each component is deterministically tagged Material / Labour / Plant / Consumable, so the downstream material & labour schedule is split correctly rather than re-guessed.

## 5.4 Profit-margin analysis (proposed vs actual)

Separate from the per-rate profit %, the platform computes project profitability per takeoff line: proposed revenue (sell rate × qty) vs proposed cost (net × (1 + overhead%) × qty), giving proposed profit and margin %, with an actual side that uses re-measured rate/qty. Aggregated across the project, this reports total proposed vs actual profit and the variance — surfaced at unified save time as a margin summary.

## 5.5 Where rates are managed

End-users browse their effective rate library on the web (a live, auto-refreshing dashboard with tabs for Master Materials/Labour, My Materials/Labour, My Custom Rates, and Effective Rates) and see a Rate Updates feed that badges newly changed master rates. Heavy rate editing happens in the RateGen desktop app and syncs to these endpoints. Admins curate the master catalogue and build-up rates.

# 6. Material & Labour schedules with pricing

The Materials view turns the takeoff into a priced material & labour schedule — the procurement and pricing companion to the structural BOQ.

- One line per material/labour component. The takeoff is grouped by material (e.g. "Cement", "Sandcrete Block 9in", "Reinforcement Y12"), each with its quantity, unit, and an editable rate.

- Priced from Rate Gen's component catalogue. Rates here come from the material + labour master/user price lists (not composite build-up rates). For each line the platform proposes the best-matching catalogue price, honouring the required unit and preferring the user's own library over the master.

- One-click auto-fill & price sync. "Auto-fill (RateGen)" prices every line against the catalogue (optionally only empty rates, never overwriting on a unit conflict); "Sync prices" keeps them current.

- Procurement tracking. The same grid drives a Purchased status (instead of "Completed"), so the material schedule doubles as a purchase/earned tracker: qty × rate = amount, with valued/balance per line.

The connection to Rate Gen is two-tiered: the Materials view prices against component (material + labour) rates, while the BOQ view prices against composite build-up rates — both sourced from the same Rate Gen library.

# 7. Contract Tracker

The contract tracker turns a priced BOQ into a frozen contract baseline and then polices every subsequent change against it — the mechanism that makes the platform a genuine contract-administration tool, not just an estimating sheet.

## 7.1 Locking the contract

When the bill is agreed, the user locks the contract behind a 4-digit PIN (stored hashed, never returned to the browser). Locking:

- Snapshots every line (description, qty, unit, rate) as the contract baseline.

- Freezes the grand-summary cascade at that moment — measured work, provisional, preliminaries, contingency, VAT, and the resulting contract sum — and stores each frozen component.

Unlocking requires the matching PIN (contracts locked before the PIN feature unlock without one, for back-compatibility). Unlocking clears the lock and PIN but keeps the baseline and contract sum for history, so re-locking sets a fresh PIN.

## 7.2 What the lock enforces

Once locked, the priced structural scope is protected — and the enforcement is server-side and authoritative, so it holds even if a client tries to bypass a disabled field:

- New lines added after lock are not added to measured work — they are automatically diverted into the Variation tracker as post-lock-new-item change orders.

- Re-measured quantity → the new figure is written to Actual qty while the contract qty snaps back to the baseline. The variance becomes a claimable item without losing the baseline.

- Re-priced rate → same pattern: the new rate goes to Actual rate, the contract rate reverts to baseline.

- Delete protection — any baseline line omitted from a save is re-inserted (with its prior actuals/progress), so the contract sum can never silently shrink.

Editable while locked: rate (recorded as actual), actual qty/rate, category/trade, and completion status. Everything that would move the contract sum is captured as a tracked variance instead.

The result: the contract sum stays stable, while every deviation from it is surfaced and tracked.

# 8. Variation Tracker

Variations are the controlled channel for change after the contract is set. Each variation carries: description, qty, unit, rate, reference, issued date, a source (manual or post-lock-new-item), and a completed flag. Its value is qty × rate.

- Manual variations — the QS keys them directly into the BOQ's Variations section (reference, description, qty, unit, rate, date).

- Automatic variations — as described above, any line added to a locked contract is automatically captured as a variation with reference AUTO, so out-of-contract scope can never slip into measured work unnoticed.

- Roll-up rules — variations always count toward the project total (and toward EVM's Budget at Completion), but count as earned value only when marked completed. The same semantics apply to provisional sums.

- Progress propagation — when a WBS task linked to a variation reaches 100%, the variation is automatically flipped to completed.

A Contract Movement panel on the PM dashboard visualises variations declared vs executed, PC sums released, and the forecast final cost vs the contract sum (savings or over-run).

# 9. Interim Valuation & Payment Certificates

The platform issues proper interim payment certificates on the cumulative-less-previous basis, with full retention/VAT/WHT handling.

## 9.1 How a certificate is computed

Issuing a certificate computes the cumulative value to date across all streams:

- Measured work — Σ (actual or planned qty) × (actual or planned rate) × valuationFactor, so partial progress flows in (a line at 60% contributes 60%).

- Variations — completed variations only.

- Provisional sums — completed only.

- Preliminaries — the preliminary pool × the completed allocation.

Then the certificate arithmetic:

This certificate = max(0, Cumulative value − Σ previous certificates) Retention = This certificate × Retention% Net before tax = This certificate − Retention + Retention released VAT = Net before tax × VAT% WHT = Net before tax × WHT% Net payable = Net before tax + VAT − WHT

Retention/VAT/WHT rates default from the project's valuation settings and are captured at issue, so historical certificates remain reproducible even if rates later change. Certificates are numbered automatically.

## 9.2 Certificate lifecycle

- Status — each certificate is draft → approved → paid, set from a per-row dropdown.

- Immutable financials — once issued, only status/notes/dates can be edited; the money is frozen.

- Safe deletion — only the latest certificate can be deleted, preserving the cumulative chain.

- Export — certificates export to Excel; the valuation tab can also produce a printable Interim Payment Application from the daily valuation log.

- A totals footer shows total certified and net retention held.

## 9.3 Final account

When work is complete, the project is closed out with a Final Account that snapshots final measured work, provisional, preliminaries and variations; sums retention released and total certified to date; and computes:

Final contract value = Measured + Provisional + Preliminary + Variations Savings = Agreed contract sum − Final contract value (positive = under-run)

Finalising freezes the project (no further certificates or BOQ edits); it can be reopened if needed.

# 10. Project Management — WBS & linking cost with WBS

The PM layer turns the priced BOQ into a costed work programme. Its defining capability is linking cost to the Work Breakdown Structure, so schedule progress and commercial value stay reconciled.

## 10.1 The WBS / task model

Each task carries a dotted WBS code (e.g. A.21.1), name, schedule (start/end, baseline start/end, duration, actuals), predecessors, critical-path flag, % complete, status, priority, and cost links.

## 10.2 Three ways to build the WBS

- Manual — add tasks with a WBS code, dates, priority, milestone/critical-path flags, and either a manual ₦ cost or BOQ links.

- Generate from BOQ — one task per BOQ line, auto-linked, with baselineCost = qty × rate and dates distributed across the programme window. Re-running updates existing tasks rather than duplicating.

- Import MS Project — upload a .xml (or .mpp) programme. The importer reads dates, baselines, durations, % complete, WBS/outline numbers, milestones, summaries, predecessors and the critical path (from the Critical flag or zero total slack). It deliberately ignores resource-derived costs (importing only explicit baseline costs) so your cost baseline stays clean.

## 10.3 Linking cost to the WBS (the core feature)

Tasks link to one or more BOQ lines — measured items, preliminaries, PC sums, or variations — through a searchable picker. The differentiator is weighting:

- A single BOQ line can be split across several tasks by weight (e.g. an electrical line as first-fix 70% / final-fix 30%).

- A task's baseline cost is the weighted sum of its linked lines: Σ item.amount × weight%.

- A WBS-link health chip on each BOQ row shows whether that line is fully allocated (emerald = 100%), under-allocated (a WBS gap), or over-allocated (a double-count risk).

Smart auto-linking matches imported task names to BOQ items using (a) per-user learned mappings that improve over time and (b) fuzzy matching, reporting how many links were made. Re-importing an updated programme smart-merges: schedule fields refresh from MS Project while progress, cost links and manual edits are preserved.

## 10.4 WBS roll-ups & scheduling

- Summary tasks roll up their leaf descendants — baseline/actual cost, weighted % complete, and earliest-start/latest-finish — purely from the WBS code hierarchy.

- Auto-reschedule — changing the project start cascades dates through the network (finish-to-start, cycle-safe), and a manual reschedule recalculates the whole programme.

- A BOQ heatmap renders every line as a colour-coded progress cell (grouped by category/trade), giving an at-a-glance picture of where work stands.

- A calendar export (.ics) puts the programme into any calendar app.

# 11. Earned Value Management (EVM)

Because cost is linked to the WBS, the platform produces genuine earned-value project controls on the PM dashboard.

| Metric | Meaning | How it's derived |
| --- | --- | --- |
| BAC (Budget at Completion) | Total project budget | The live project total (forced to it when the contract is locked) |
| PV (Planned Value) | What should be earned by today | Schedule-based: each task's baseline cost interpolated between its baseline start/finish |
| EV (Earned Value) | Value actually delivered | BOQ-side earned value: measured (partial-aware) + completed PC/variations/preliminaries |
| AC (Actual Cost) | Spent to date | Actual costs recorded against the work |
| CPI | Cost performance | EV / AC |
| SPI | Schedule performance | EV / PV |
| EAC | Forecast final cost | BAC / CPI |
| VAC | Forecast variance | BAC − EAC |

The dashboard surfaces six headline tiles (Progress %, Budget Used %, Overdue, CPI, SPI, Tasks Done %), a budget bar (BAC/EV/AC), a tasks donut, a burndown chart (planned vs actual remaining), and a WBS health strip (status & priority mix + critical-path banner).

A standout integrity feature is the BOQ↔WBS coverage reconciliation: it classifies every BOQ line as unlinked, fully linked, under-linked, or over-linked, flags stale links (a task pointing at a line that was renamed or removed — which would silently drop its baseline to ₦0), and reports an overall coverage %. This catches the classic earned-value error of double-counting or missing scope.

# 12. Progress tracking & the valuation audit trail

Progress is captured as an append-only valuation ledger. Every time a line's earned position changes — a binary ratification or a % movement — the platform records a signed event (the value delta, the before/after %, and the day it was marked). Summing the positive deltas for a period gives the value of work done in that period.

These events roll into daily valuation logs (with a staleness filter so reverted lines don't linger), which power the valuation date selector and the printable interim certificate. Progress is also bi-directional: updating a WBS task's % complete propagates back to its linked BOQ lines as a weighted sum, which then flows through the same valuation pipeline — so the schedule and the bill always agree on how much has been earned.

# 13. Client sharing — the public dashboard

Any project can be shared with the client through a read-only public link (no login required). The public dashboard re-frames the QS numbers in plain client-facing language:

- An on-track / watch / over-budget status banner and a progress ring with physical and cost bars.

- The full contract-sum cascade (measured / provisional / preliminaries / contingency / VAT / variations) — showing the frozen lock-time values once the contract is locked.

- EVM in plain English — "Spent to date" (ACWP), "Value delivered" (BCWP), "Performance" (CPI), "Expected final cost" (EAC).

- A certificate roll-up — total certified, retention held, and whether the final account is open or closed.

- Any attached BIM models and an upcoming-spend view.

- A header badge showing Draft / Contract-locked / Final-account-closed.

# 14. BIM model attachments

Each project can carry up to three IFC/BIM model uploads — one each for Architectural, Structural, and MEP disciplines — stored in cloud object storage and surfaced (including on the public dashboard) so the client can see the model alongside the commercial data.

# 15. Appendix

## 15.1 Key formulas at a glance

Rate build-up

Net = Σ(component qty × unit price) Total = Net + Net×Overhead% + Net×Profit% (defaults: OH 10%, Profit 25%)

BOQ grand summary

Prelim = (Gross + Provisional) × Prelim% (default 7.5%) Subtotal = Gross + Provisional + Prelim Contingency = Subtotal × Contingency% (default 5%) VAT = (Subtotal + Contingency) × VAT% (default 7.5%) Project total = Subtotal + Contingency + VAT + Variations

Interim certificate

This cert = max(0, Cumulative value − Σ previous certs) Retention = This cert × Retention% Net before tax = This cert − Retention + Retention released Net payable = Net before tax + (Net before tax × VAT%) − (Net before tax × WHT%)

Earned value

CPI = EV/AC SPI = EV/PV EAC = BAC/CPI VAC = BAC − EAC

Per-line earned value

valuationFactor = 1 if ratified, else %complete/100 Earned = qty × rate × valuationFactor Balance = qty × rate × (1 − valuationFactor)

## 15.2 Classification taxonomy

Categories (building element)

- Structural (QUIV/HERON/CIVIQ): Substructure · Frames · Superstructure

- Services (Revit MEP): HVAC · Plumbing · Electrical

Trades (NRM2/SMM7 work sections)

- Structural: Earthworks · Concrete Works · Formwork · Reinforcement · Masonry · Damp-proofing · Carpentry & Roofing · Joinery · Finishes—Floor · Finishes—Wall · Finishes—Ceiling · Decoration · Structural Steelwork · External Works

- Services: HVAC · Plumbing & Drainage · Electrical Installations

Rate Gen sections

- Groundwork · Concrete Works · Blockwork · Finishes · Roofing · Windows & Doors · Painting · Steelwork · Carbon & Others

## 15.3 Export reference

| Output | Format | Source |
| --- | --- | --- |
| Elemental BOQ (Bungalow / Multi-storey) | Excel (formula-driven) | Server |
| Trade BOQ (NRM2-style) | Excel (formula-driven) | Server |
| Generic BOQ (by category / by trade) | Excel | Client (live on-screen rates) |
| Material & Labour schedule | Excel | Client |
| Interim payment certificate | Excel + printable HTML | Client/Server |
| Final account | Excel | Server |
| Work programme | .ics calendar | Server |

## 15.4 Standards & conventions referenced in the code

- BESMM4 — preliminaries checklist (22 standard items)

- NRM2 / SMM7 — trade/work-section structure and codes (E10/E20/E30)

- BS 4449 / BS 4483 — reinforcement bars; BS 5950 — structural steelwork

- Nigerian BOQ serial lettering — A, B, C … (skip I) … J, K …

- Currency — NGN-native throughout

This document reflects the features implemented in the ADLM Website codebase as of the current branch. Formulas, defaults, and classifications are drawn directly from the implementation.